## Schedule 2025
TD Number | PSURNumber | Class | Type | Product Name | Catalog Number | Writer | Email | Start Period | End Period | Frequency | Due Date | Status | Canada Summary Report Needed | Canada Summary Report Status | Comments
TD005 | PMS005R | I | Fertility | RI Syringes | See Appendix in PMSP | TBD | Terence.Musoni@Coopersurgical.com | 2021-06-01 | 2026-05-31 | 5 years | 2026-06-06 | Assigned | NO | TBD | Rev C is stuck in MC as Draft.
TD006 | PMS006R | I | Medical Device | Cytology Sampling Products | See Appendix in PMSP | TBD | Terence.Musoni@Coopersurgical.com | 2024-01-01 | 2029-12-31 | 5 years | 2030-01-31 | NOT DUE | YES | TBD
TD008 | PMS008R | I | Medical Device | Endosee Hysteroscopy Product Family | See PLAN Appendix | TBD | Terence.Musoni@Coopersurgical.com | 2021-01-29 | 2025-05-31 | 5 years | 2026-03-01 | Not started | NO | TBD
TD121 | PMS011R | I | Medical Device | OBP Medical Disposable Speculum (Sterile) | C020300, C020310, C020320, C020600, C020610, C020620, | TBD | Terence.Musoni@Coopersurgical.com | 2022-01-01 | 2027-12-31 | 5 years | 2027-01-01 | Not started | YES | TBD
REF-01-0001 | PMS012R | I | Medical Device | OBP Medical Endoscopic Seals | C010011 (aka. 26153EAU-10), C010012 (aka. 27550ZAG-10), C010013, C010014, C010017, C010018, C010030, C010031 | TBD | Terence.Musoni@Coopersurgical.com | 2022-01-01 | 2027-12-31 | 5 years | 2027-01-01 | Not started | NO | TBD
TD052 | PMS052R | I | Medical Device | Ally Adapter Drapes | See PLAN Appendix | TBD | Terence.Musoni@Coopersurgical.com | 2023-08-01 | 2028-07-31 | 5 years | 2027-01-01 | Not started | NO | TBD
TD064 | PMS064R | I | Medical Device | Post-Market Surveillance Report for H/S Catheter Product Family of Devices | 61-XXXX | TBD | Terence.Musoni@Coopersurgical.com | 2022-06-01 | 2027-05-31 | 5 years | 2027-01-01 | Not started | YES | TBD
TD001 | TBD | TBD | Medical Device | Doppler Components | MH-8L, SC082500, SC062500 | TBD | Terence.Musoni@Coopersurgical.com | TBD | TBD | TBD | TBD | Not started | YES | TBD
TD002 | TBD | TBD | Medical Device | LED Doppler System | 1D-12110, 1DL-LED, BG Series | TBD | Terence.Musoni@Coopersurgical.com | TBD | TBD | TBD | TBD | Not started | YES | TBD
TD083 | PMS083R | I | Medical Device | Doppler | See PLAN Appendix | TBD | Terence.Musoni@Coopersurgical.com | 2023-08-01 | 2025-07-31 | 5 years | 2027-01-01 | Not started | YES | TBD
TD120 | PMS120R | I | Medical Device | SOS Fetal Pillow | See Plan Appendix | TBD | Terence.Musoni@Coopersurgical.com | 2024-02-01 | 2029-01-31 | 5 years | 2027-01-01 | Not started | YES | TBD
TD123 | PMS123R | I | Fertility | K-Systems Flex Short-term Incubator Module | See Appendix in PMSP | TBD | Terence.Musoni@Coopersurgical.com | 2022-01-01 | 2027-12-31 | 5 years | 2029-01-01 | Not started | NO | TBD
TD125 | PMS125R | I | Medical Device | Endo Kit | See Plan Appendix | TBD | Terence.Musoni@Coopersurgical.com | 2023-01-01 | 2028-12-31 | 5 years | 2027-01-01 | Not started | NO | TBD
TD004 | PMSR004 | I | Medical Device | CODA Air Filtration System | See PLAN Appendix | TBD | Terence.Musoni@Coopersurgical.com | 2021-05-01 | 2026-04-30 | 5 years | 2027-01-01 | Not started | NO | TBD
TD017 | PMSR017 | I | Fertility | EZ-Grip & Comfort Rest | See Appendix in PMSP | TBD | Terence.Musoni@Coopersurgical.com | 2021-01-01 | 2025-12-31 | 5 years | 2027-01-01 | Not started | NO | TBD
TD003 | TBD | TBD | Medical Device | UPS Systems | AU-UPS | TBD | Terence.Musoni@Coopersurgical.com | TBD | TBD | TBD | TBD | Not started | YES | TBD
TD124 | PMSR124 | I | Medical Device | Biopsy Kit | See Plan Appendix | TBD | Terence.Musoni@Coopersurgical.com | 2022-01-01 | 2027-12-31 | 5 years | 2027-01-01 | Not started | NO | TBD
TD007 | TBD | TBD | TBD | TBD | 3301G, 3302G, 3304G | TBD | Terence.Musoni@Coopersurgical.com | TBD | TBD | TBD | TBD | Not started | YES | TBD
TD009 | TBD | TBD | TBD | TBD | 42-1820, 42-2540 | TBD | Terence.Musoni@Coopersurgical.com | TBD | TBD | TBD | TBD | Not started | YES | TBD
TD010 | PMS010 | TBD | TBD | INCA | 025-009, 44-2707 | TBD | harish.gyanaji@coopersurgical.com | 2020-04-02 | 2025-06-30 | TBD | TBD | Assigned | YES | TBD
TD011 | PSUR011 | III | Media | Biopsy Medium | 10620010 | Venkata SD | venkata.dommeti@coopersurgical.com | 2022-07-01 | 2024-06-30 | Annually | 2025-08-15 | PMS Section Done, pending clin | NO | TBD | Surveillance Period : 1-Jul-22 to 30-Jun-24 has been released already. Current Surveillance Period: 01-Jul-2024 to 30 -Jun-2025 - VSD
TD012 | TBD | TBD | TBD | TBD | 120-239, CE-2000 | TBD | Terence.Musoni@Coopersurgical.com | TBD | TBD | TBD | TBD | Not started | YES | TBD
TD013 | TBD | TBD | TBD | TBD | 900200AA-900215AA | TBD | Terence.Musoni@Coopersurgical.com | TBD | TBD | TBD | TBD | Not started | YES | TBD
TD014 | TBD | TBD | TBD | TBD | 900108, 900111 | TBD | Terence.Musoni@Coopersurgical.com | TBD | TBD | TBD | TBD | Not started | YES | TBD
TD019 | PSUR019 | III | Media | Blast Freeze/BlastThaw | 1054 | Jeff S | jeffrey.spivak@coopersurgical.com | 2024-01-01 | 2024-12-31 | Annually | 2025-01-15 | Released | NO | TBD | Released 2-21-25
TD020 | PSUR020 | III | Media | TD020 - Flushing Medium (1084) Flushing Medium with Heparin (1076) | 10760125, 10765060, 10840125, 10845060 | Harish G | harish.gyanaji@coopersurgical.com | 2024-01-01 | 2024-12-31 | Annually | 2025-07-15 | RELEASED | YES | TBD
TD015 | PSUR015 | IIa | Medical Device | Uterine Manipulators and Accessories Product Family | See PLAN Appendix | TBD | TBD | 2022-04-01 | 2024-03-31 | Biennial | 2025-07-30 | Not started | YES | TBD
TD022 | PSUR022 | III | Media | Embryo Freezing & Thawing Pack | 10264010, 10984010 | Venkata SD, Pranavi | Pranavi.vutukuru@coopersurgical.com | 2024-07-01 | 2025-06-30 | Annually | 2025-08-15 | Released | NO | TBD | Routing in MC - VSD 28APR2025
TD016 | PSUR016 | IIb, III | Fertility | PICSI® Sperm Selection Device | BCT-PICSI-20 | Harish G | harish.gyanaji@coopersurgical.com | 2024-04-01 | 2025-03-31 | Annually | 2025-09-15 | In Progress | NO | TBD
TD025 | PSUR025 | III | Media | ICSI Cumulase | 16125000 | Harish G | harish.gyanaji@coopersurgical.com | 2024-01-01 | 2024-12-31 | Annually | 2025-04-10 | Released | NO | TBD | In work
TD026 | PSUR026 | III | Media | MediCult IVM® System (8221) | 82214010 | Jeff S | jeffrey.spivak@coopersurgical.com | 2024-01-01 | 2024-12-31 | Annually | 2025-03-10 | Released | NO | TBD
TD028 | PSUR027 | III | Media | PVP Clinical Grade (1090) | 10905000 | Venkata SD, Heather H | venkata.dommeti@coopersurgical.com | 2024-01-01 | 2024-12-31 | Annually | 2025-01-22 | Released | NO | TBD
TD028 | PSUR028 | III | Media | PVP Medium (1089) | 10890001 | Venkata SD | venkata.dommeti@coopersurgical.com | 2024-01-01 | 2024-12-31 | Annually | 2025-04-01 | Released | NO | TBD
TD021 | PSUR029 | III | Media | Sperm Freezing Medium (1067) | 10670010 | Venkata SD | venkata.dommeti@coopersurgical.com | 2024-01-01 | 2024-12-31 | Annually | 2025-04-01 | Released | NO | TBD
TD094 | PSUR030 | III | Media | Origio Sperm Preparation Medium (1069/1070) | (1069/1070) | TBD | TBD | 2024-02-01 | 2025-01-31 | Annually | 2025-03-15 | Released | NO | TBD | Draft in sharepoint
TD031 | PSUR031 | III | Media | SpermSlow™ (1094) | 10944000 | Harish G | harish.gyanaji@coopersurgical.com | 2024-01-01 | 2024-12-31 | Annually | 2025-01-13 | Released | NO | TBD | Released
TD020 | PSUR032 | III | Media | SynVitro Flush (1584) | 1584 | Jeff S | jeffrey.spivak@coopersurgical.com | 2024-01-01 | 2024-12-31 | Annually | 2025-05-03 | Released | YES | TBD | Released 5-13-25
TD033 | PSUR033 | III | Media | Universal IVF Medium (1030 & 1031) | 1030, 1031 | Jeff S | jeffrey.spivak@coopersurgical.com | 2024-01-01 | 2024-12-31 | Annually | 2025-01-31 | Released | NO | TBD | Approved and Released 2-5-25
TD018 | PSUR018 | IIb | Medical Device | LEEP ELECTRODES | See PLAN Appendix | TBD | Terence.Musoni@Coopersurgical.com | 2023-06-01 | 2025-05-31 | Annually | 2025-07-16 | Not started | YES | TBD
TD035 | PSUR035 | III | Media | ORIGIO® Sequential Blast™ | 83050010, 83050060, 83060010, 83060060 | Venkata SD | TBD | 2023-07-01 | 2024-06-30 | Annually | 2025-01-17 | Released | NO | TBD | Rev C released in MC with the same time frame
TD036 | PSUR036 | III | Media | ORIGIO® Sequential Cleav™ | 83030010, 83030060, 83040010, 83040060 | Jeff S | jeffrey.spivak@coopersurgical.com | 2024-01-01 | 2024-12-31 | Annually | 2025-04-15 | Released | NO | TBD | Released 3-27-25
TD037 | PSUR037 | III | Media | ORIGIO® Sequential Fert™ | 83010010, 83010060, 83020010, 83020060 | Venkata SD | venkata.dommeti@coopersurgical.com | 2024-01-01 | 2024-12-31 | Annually | 2025-07-28 | Released | YES | TBD
TD020 | PSUR023 | III | Media | SynVitro Flush with Heparin (1576) w/o Heparin (1584) | 1576, 1584 | Terence | Terence.Musoni@Coopersurgical.com | 2024-01-01 | 2024-12-31 | Annually | 2025-07-14 | Pending clinical Stakeholder Review
TD020 | PSUR300 | III | Media | LG global collect 100 ml (GCOL-100), 500 ml (GCOL-500) | GCOL-100, GCOL-500 | Venkata SD | venkata.dommeti@coopersurgical.com | 2024-01-01 | 2024-12-31 | Annually | 2025-06-06 | Stakeholder Review | YES | TBD | Report Completed waiting on risk files to be released - VSD
TD021 | PSUR021 | III | Media | Cryosperm (1101) | 11010010 | TBD | Terence.Musoni@Coopersurgical.com | 2024-01-01 | 2024-12-31 | Annually | 2025-04-15 | Assigned | NO | TBD
TD041 | PSUR041 | IIa | Media | Liquid Paraffin - CHANGE CURRENT REV C TO B AND B TO A | 1010 | Jeff S | jeffrey.spivak@coopersurgical.com | 2023-07-02 | 1990-06-30 | Biennial | 2025-02-19 | Released | YES | TBD | Created a new InfoCard TD155. Main file is Revision B. No other revision changes.
TD021 | PSUR201 | III | Media | Quinn’s Advantage™ Sperm Freezing Medium (ART-8022) | ART-8022 | TBD | TBD | 2024-01-01 | 2024-12-31 | Annually | 2025-04-01 | Stakeholder Review | NO | TBD
TD034 | PSUR034 | III | Media | UTM™ Transfer Medium (1052/1152) | 10520010, 11520010 | Terence | terence.musoni@coopersurgical.com | 2024-01-01 | 2024-12-31 | Annually | 2025-03-17 | Drafting | NO | TBD
TD035 | PSUR204 | III | Media | Quinn’s Advantage™ Blastocyst Medium (ART-1029) | ART-1029 | Harish G | harish.gyanaji@coopersurgical.com | 2024-07-01 | 2025-06-30 | Annually | 2025-08-31 | In Progress | NO | TBD | In Progress
TD045 | PSUR045 | III | Media | ORIGIO® Handling™ | 83100060, 83100125, 83110060, 83110125 | TBD | TBD | 2023-08-01 | 2024-07-31 | Annually | 2025-04-09 | RELEASED | YES | TBD
TD036 | PSUR208 | III | Media | Quinn’s Advantage™ Cleavage Medium | ART-1026, ART-1027 | TBD | TBD | 2024-01-01 | 2024-12-31 | Annually | 2025-06-06 | Not started | NO | TBD
TD089 | PSUR046 | III | Media | Sage 1-Step GM-CSF | 77010003 | Harish G | harish.gyanaji@coopersurgical.com | 2024-07-01 | 2025-06-30 | Annually | 2025-07-18 | RELEASED | YES | TBD | crossfunctional review
TD037 | PSUR206 | III | Media | Quinn’s Advantage™ Fertilization (HTF) Medium and Quinn’s Advantage™ Protein Plus Fertilization (HTF) Medium | ART-1520, ART-1020, ART-1021 | TBD | TBD | 2024-01-01 | 2024-12-31 | Annually | 2025-09-18 | Not started | YES | TBD | Data analyzed in sharepoint
TD037 | PSUR304 | III | Media | Global® for Fertilization and Global® total® LP for Fertilization | (LGGF-020), 50 ml (LGGF-050), 100 ml (LGGF-100), (H5TF-010), 20 ml (H5TF-020), 50 ml (H5TF-050), 100 ml (H5TF-100) | Harish G | harish.gyanaji@coopersurgical.com | 2024-01-01 | 2024-12-31 | Annually | 2025-11-09 | In Progress | YES | TBD
TD039 | PSUR039 | III | Media | Acidified Tyrodes Solution (1060) | 1060 | Harish G | harish.gyanaji@coopersurgical.com | 2024-07-01 | 2025-06-30 | Annually | 2025-08-31 | In Progress | NO | TBD | In Progress
TD050 | PSUR050 | IIa | Fertility | RI Witness EHP | 6-70-807, 6-70-807-A, 6-70-807-B | TBD | Terence.Musoni@Coopersurgical.com | 2022-03-01 | 2024-02-28 | Biennial | 2025-04-21 | Released | NO | TBD
TD041 | PSUR041 | Non-EU MDR | Media | Qa BLASTOCYST MEDIUM | ASSIGN DIFFERENT NUMBER | Harish G | harish.gyanaji@coopersurgical.com | TBD | TBD | TBD | No update needed-See comments | No update needed-See comments | YES | TBD | No update needed- Terence comments : Line item for QA blastocyst medium is a registration report for Saudi that Terence did. Its probably this one. PSUR for Quinn's Advantage Protein Plus Blastocyst Medium(1529).docx It should not be part of a TD. So it does not need renewal right now.
TD053 | PSUR053 | III |  | INSORB Skin Stapler and Forceps | 2030, 9100 | Terence | Terence.Musoni@Coopersurgical.com | 2024-01-01 | 2024-12-31 | Annually | late | Released | YES | TBD | PSUR053 Rev C is released for surveillance period July 2017 through April 2023
TD041 | PSUR205 | IIa | Media | Oil for tissue Culture | (ART-4008P) (ART-4008-5P) | Jeff S | jeffrey.spivak@coopersurgical.com | 2024-07-01 | 2026-06-30 | Biennial | TBD | Assigned | YES | TBD
TD059 | PSUR059 | Is | Medical Device | Assisted Reproduction Catheters | See Plan Appendix | TBD | Terence.Musoni@Coopersurgical.com | TBD | TBD | 5 years | 2027-01-31 | Assigned | YES | TBD
TD060 | PSUR060 | IIa |  | Carter-Thomason Port Closure Products | See PMS Plan |  |  | 2019-08-01 | 2024-07-31 | Biennial |  | Released
TD062 | PSUR062 | I | Medical Device | Endometrial Suction Curette Product Family | MX120, MX124, MX130, MX140, MX145, MX150, 8200, 90814A, 908015, 908016 | TBD | Terence.Musoni@Coopersurgical.com | 2023-10-01 | 2028-09-30 | 5 years | 2027-01-01 | Not started | YES | TBD
TD066 | PSUR066 | IIa | Fertility | IVF Incubators | G210 | Harish G | harish.gyanaji@coopersurgical.com | 2023-01-01 | 2024-12-31 | Biennial | 2025-02-15 | Released | NO | TBD | Q1 Pending-Routing in Master Control-21 Mar 2025
TD069 | PSUR069 | IIa | Fertility | Lone Star Elastic Stays | See PMS Plan | Jeff S | jeffrey.spivak@coopersurgical.com | 2022-04-01 | 2024-03-31 | Biennial | 2025-07-09 | Released | YES | TBD | Released 8-4-25
TD041 | PSUR301 | IIa | Media | LifeGuard® Oil | 100 ml (LGUA-100), 500 ml (LGUA-500), 100 ml - Amber Bottle (AMLG-100) | Venkata SD | venkata.dommeti@coopersurgical.com | 2024-01-01 | 2025-12-31 | Biennial | 2025-03-05 | Assigned | YES | TBD | PSUR301 Rev C for Surveillance Period 01-Jun-2021 to 31-Dec-2023 is released in Jan 2025, the next report needs to be released in 2026 - VSD 21MAR2025
TD073 | PSUR073 | IIa | Medical Device | IVF PASTEUR PIPETTES | PP-5.75-90, PP-5.75-1000, PP-5.75-90PL, PP-5.75-1000PL, PP-9-90, PP-9-1000, PP-9-90PL, PP-9-1000PL | Harish G | harish.gyanaji@coopersurgical.com | 2024-07-01 | 2026-06-30 | Biennial | 2026-08-06 | Not started | NO | TBD
TD076 | PSUR076 | IIa | Medical Device | Vacuum Assisted Delivery System | 10004, 10007LP, 10008, 10020, 10137, 10022, 10057, 10058, 10067, 10068 | Jeff S | jeffrey.spivak@coopersurgical.com | 2024-06-01 | 2026-05-31 | Biennial | 2026-08-13 | Assigned | YES | TBD
TD041 | PSUR302 | IIa | Media | LiteOil® | (LGOL-100), 500 ml (LGOL-500), 100 ml - Amber Bottle (AMLO-100) | TBD | TBD | 2021-07-01 | 2023-12-31 | Biennial | INVESTIGATE | Assigned | YES | TBD
TD041 | PSUR303 | IIa | Media | Paraffin Oil P.G. | 100 ml (LGPO-100), 500 ml (LGPO-500), 100 ml - Amber Bottle (AMPO-100) | TBD | Terence.Musoni@Coopersurgical.com | 2024-01-01 | 2024-12-31 | Biennial | 2025-01-19 | Assigned | YES | TBD
TD044 | PSUR044 | IIa | Media | VitriFit™ | 4278, 4279, 4280, 4281, 4282, 8284, 4285, 4286 | Venkata SD | venkata.dommeti@coopersurgical.com | 2023-07-03 | 2025-06-30 | Biennial | TBD | Assigned | YES | TBD
TD087 | PSUR087 | IIa | Media | LifeGlobal Dishes GPS® Dishware | 4GPS-010,EGPS-010,EMBC-010,MGPS-010 MI38-010,SP38-010,UGPS-010 | Harish G | harish.gyanaji@coopersurgical.com | 2024-06-01 | 2026-05-31 | Biennial | 2026-08-20 | Not started | NO | TBD
TD045 | PSUR045 | III | Media | ORIGIO® Handling™ | 83100060, 83100125, 83110060, 83110125 | TBD | TBD | 2024-08-01 | 2025-07-31 | Annually | 2025-09-01 | Assigned | YES | TBD
TD092 | PSUR092 | III | Media | Medicult Vitrification Cooling, MediCult Vitrification Warming | 1228, 1229 | Harish G | harish.gyanaji@coopersurgical.com | 2024-01-01 | 2024-12-31 | Annually | 2025-02-15 | Released | YES | TBD | Q1 Pending-In work-In crossfunctional review; Needs discussion on review period for summary report
TD094 | PSUR094 | III | Media | Origio Sperm Wash (8405) | 84050010, 84050060, 84051010, 84055060 | Venkata SD | venkata.dommeti@coopersurgical.com | 2024-01-01 | 2024-12-31 | Annually | 2025-01-17 | Released | NO | TBD
TD095 | PSUR095 | III | Media | ORIGIO® Gradient™ 100, ORIGIO® Gradient™ 90 , and ORIGIO® Gradient™ 40/80 / Density gradient product family | 84000060, 84000125, 84002060, 84004125, 84010060, 84021210, 84022010, 84022060 | Harish G | harish.gyanaji@coopersurgical.com | 2024-01-01 | 2024-12-31 | Annually | 2025-03-15 | Released | NO | TBD | Q1 Pending-crossfunctional review
TD102 | PSUR102 | III | Media | EmbryoGen, BlastGen, EmbryoGen® & BlastGen | 1204 | Pranavi | Prinavi.vutukuru@coopersurgical.com | 2024-05-01 | 2025-04-30 | Annually | 2025-05-31 | Released | NO | TBD
TD045 | PSUR214 | III | Media | Quinn’s Advantage Medium with HEPES | ART-1023A, ART-1023F, ART-1024A, ART-1024F | TBD | TBD | 2024-08-01 | 2025-07-31 | Annually | 2025-09-05 | Assigned | YES | TBD
TD045 | PSUR311 | III | Media | LG global w/ HEPES | LGGH-050, LGGH-100, LGGH-250, LGGH-500 | Jeff S | jeffrey.spivak@coopersurgical.com | 2024-07-01 | 2025-06-30 | Annually | 2025-08-01 | MasterControl Routing | YES | TBD | Stakeholder review 8-8-25 Update: Waiting to route in MC until PMCF-LRR 2025-01 is released. Routing for approval in MasterControl 9-30-25
TD118 | PSUR118 | I | Medical Device | OBP AnoSpec Lighted Anoscopes | C060100, C060110, and C060120 | TBD | Terence.Musoni@Coopersurgical.com | TBD | TBD | 5 years | 2028-01-01 | Not started | YES | TBD
TD121 | PSUR121 | I | Medical Device | Lighted Vaginal Speculums | See Plan Appendix | TBD | Terence.Musoni@Coopersurgical.com | TBD | TBD | 5 years | 2028-01-01 | Not started | YES | TBD
TD122 | PSUR122 | I | Medical Device | Lighted Endoscopic Products | See Plan Appendix | Harish G | harish.gyanaji@coopersurgical.com | TBD | TBD | 5 years | 2027-01-01 | Not started | YES | TBD | PMSR122 Rev A is released for Self-Sealing Endoscopic Seal, does both the products are same?
TD129 | PSUR129 | Iib | Medical Device | Cook Doppler blood flow monitor products |  | Venkata SD, Karen K | venkata.dommeti@coopersurgical.com | 2019-09-01 | 2024-08-31 | Annually | 2025-01-31 | Released | TBD
TD130 | PSUR130 | IIa | Medical Device | TD130 Bakri Postpartum Balloon | See Plan Appendix | Harish G | harish.gyanaji@coopersurgical.com | TBD | TBD | Biennial | 2026-06-30 | Not started | NO | TBD
TD131 | PSUR131 | IIa | Medical Device | TD131_Cervical Ripening Balloon (CRB) Products | See Plan Appendix | Harish G | harish.gyanaji@coopersurgical.com | TBD | TBD | Biennial | 2026-06-30 | Not started | NO | TBD
TD132 | PSUR132 | Iib | Medical Device | LapSac Surgical Tissue Pouch Products | J-LS-050201, J-LS-060401, J-LS-080500, J-LS-081000 | Venkata SD | venkata.dommeti@coopersurgical.com | 2020-02-01 | 2025-01-31 | Annually | 2025-03-14 | Released | TBD
TD141 | PSUR141 | I, IIa | Medical Device | Zymot | TBD | TBD | TBD | 2018-01-01 | 2024-09-30 | Biennial | INVESTIGATE | Released | NO | TBD | PMSP 141P released , PSUR in the future
TD046 | TBD | TBD | TBD | TBD | TBD | TBD | Terence.Musoni@Coopersurgical.com | TBD | TBD | TBD | TBD | Not started | YES | TBD
TD028 | PSUR200 | III | Media | PVP™ 7% Ready to Use Solution Kit (ART-4005-A) | ART-4005-A | TBD | TBD | 2024-01-01 | 2024-12-31 | Annually | 2025-02-04 | Released | NO | TBD
TD047 | PSUR047 | III | Media | SynVitro® Hyadase | 15115001,15115001C, 15115001D, 15115001F, 15115001J,15135001 | Jeff S | jeffrey.spivak@coopersurgical.com | 2024-07-01 | 2025-06-30 | Annually | 2025-08-20 | PMS Section Done, pending clin | YES | TBD | Document is being updated with changes from Bibi. Final review to come. 9-16-25
TD048 | PSUR048 | IIa | Fertility | Integra 3 Micromanipulator | See Appendix in PMSP | TBD | TBD | 2024-07-01 | 31 June 2026 | Biennial | 2025-05-21 | Not started | NO | TBD
TD049 | PSUR049 | IIb | Fertility | Saturn 5 Laser System | 6-47-xxx-x | TBD | Terence.Musoni@Coopersurgical.com | 2024-01-01 | 2024-12-31 | Annually | 2025-05-28 | Not started | YES | TBD
TD051 | PSUR051 | IIb | Fertility | EZ-Range Pipettes | See Appendix in PMSP | TBD | Terence.Musoni@Coopersurgical.com | 2024-03-01 | 2025-02-28 | Annually | 2025-03-15 | Assigned | NO | TBD
TD054 | TBD | TBD | TBD | ABBI System | ABBI, ABBI-KIT | TBD | Terence.Musoni@Coopersurgical.com | TBD | TBD | TBD | TBD | Not started | YES | TBD
TD055 | TBD | TBD | TBD | TBD | 47-9005 | TBD | Terence.Musoni@Coopersurgical.com | TBD | TBD | TBD | TBD | Not started | YES | TBD
TD095 | PSUR209 | III | Media | PureCeption 24-determination Kit, 40% Upper Phase, 80% Lower Phase, 100% Isotonic Solution | ART-2024, ART-2040, ART-2080, ART-2100 | Jeff S | jeffrey.spivak@coopersurgical.com | 2024-01-01 | 2024-12-31 | Annually | 2025-02-19 | Released | NO | TBD
TD057 | TBD | TBD | TBD | TBD | 9022, 12021, 15021 | TBD | Terence.Musoni@Coopersurgical.com | TBD | TBD | TBD | TBD | Not started | YES | TBD
TD092 | PSUR213 | III | Media | Sage™ Vitrification Kit (ART-8026), Sage™ Vitrification Warming Kit, Sage ViaBl SuperFast Blastocyst Warming Media (ART-8035) | ART-8026, ART-8031, ART-8034, ART-8035 | Jeff S | jeffrey.spivak@coopersurgical.com | 2024-01-01 | 2024-12-31 | Annually | 2025-02-07 | Released | YES | TBD | Released 7-31-25
TD058 | PSUR058 | I | TBD | Apple-Hunt Trocars | 900-800 Series | TBD | TBD | TBD | TBD | TBD | 2025-06-25 | Not started | YES | TBD
TD060 | TBD | TBD | TBD | Carter-Thomason Port Closure Products | CTI Series, PG Series | TBD | Terence.Musoni@Coopersurgical.com | TBD | TBD | TBD | TBD | Not started | YES | TBD
TD065 | PMS065R | Is | Fertility | Intrauterine Insemination (IUI) Catheter | 7033, AIC18, SM Series | TBD | Terence.Musoni@Coopersurgical.com | TBD | TBD | TBD | TBD | Not started | YES | TBD | Is this is PSUR065 for IUI Catheters and surveillance period 1/1/2018 to 12/31/2023
TD066 | PMSR066 | IIa | Medical Device | K-Systems | K59500, K60000, K22200-110, K22200-230, K22400-110, K22400-230 | Venkata SD | venkata.dommeti@coopersurgical.com | 2023-01-01 | 2024-12-31 | Biennial | 2025-07-23 | Routing | NO | TBD | These Model PNs are covered in PSUR066 and currnetly document is routing in MC - VSD 01AUG2025
TD070 | PMS070 | IIa | Medical Device | Medical Heatpacks | 20418 and 20421 | Venkata SD | venkata.dommeti@coopersurgical.com | 2023-07-01 | 2025-06-30 | Biennial | 2025-06-18 | Not started | NO | TBD
TD071 | PSUR071 | IIa |  | Mobius Elastic Retractors | See PMS Plan | [9 empty] | PSUR071 Rev A is released for surveillance period May 2018 to May 2023
TD071 | TBD | TBD | TBD | TBD | 900-500 Series | TBD | Terence.Musoni@Coopersurgical.com | TBD | TBD | TBD | TBD | Not started | YES | TBD
TD072 | TBD | TBD | TBD | TBD | 1176 | TBD | Terence.Musoni@Coopersurgical.com | TBD | TBD | TBD | TBD | Not started | YES | TBD
TD089 | PSUR308 | III |  | LG Global | See PMS Plan | Venkata SD | venkata.dommeti@coopersurgical.com | 2024-07-01 | 2025-06-30 | Annually | 2025-08-13 | Released |  |  | NEEDED FOR SSCP Scope H5GT-010, H5GT-030, H5GT-060, H5GT-100 are covered in PSUR309 - VSD 01 AUG 2025 PSUR308 is covered under PSUR309, PSUR308 will be obsoleted once after the confirmation from RA - VSD 21AUG2025
TD089 | PSUR309 | III | Media | LG global total LP | H5GT-010, H5GT-030, H5GT-060, H5GT-100, LGGG-020, LGGG-050, LGGG-100 | Harish G | harish.gyanaji@coopersurgical.com | 2024-01-01 | 2024-12-31 | Annually | 2025-07-15 | Released | YES | TBD | NEEDED FOR SSCP
TD045 | PSUR310 | III | Media | LG global total LP w/ HEPES | 20 ml (H5TH-020), 50 ml (H5TH-050), 100 ml (H5TH-100), 250 ml (H5TH-250) | Harish G | harish.gyanaji@coopersurgical.com | 2024-01-01 | 2024-12-31 | Annually | 2025-04-23 | Released | YES | TBD
TD077 | PSUR077 | IIa | Medical Device | Wallace Oocyte Recovery/Collection Sets | ON1633, ON1733 ONS1633, ONS1633-500, ONS1633-750, ONS1633LL, ONS1633LL 500, ONS1633LL-750, ONS1733, ONS1733-500, ONS1733-750, ONS1733LL, ONS1733LL-500, ONS1733LL-750, ONS1833, ONS1833-500, ONS1833-750, ONS1833LL, ONS1833LL 500, ONS1833LL-750 DNS1633-500, DNS1633-750, DNS1633-950, DNS1733-500, DNS1733-750, DNS1733-950 | Venkata SD | venkata.dommeti@coopersurgical.com | 2022-04-01 | 2025-01-31 | Biennial | INVESTIGATE | Inprogress | YES | TBD | Revised data has been received and inprogress - VSD 3JUL2025
TD045 | PSUR311 | III | Media | LG global w/ HEPES | LGGH-050, LGGH-100, LGGH-250, LGGH-500 | Jeff S | jeffrey.spivak@coopersurgical.com | 2022-07-01 | 2024-06-30 | Annually | 2025-04-30 | Released | YES | TBD | Released 4-15-25
TD078 | TBD | TBD | TBD | TBD | 920019, 920008 | TBD | Terence.Musoni@Coopersurgical.com | TBD | TBD | TBD | TBD | Not started | YES | TBD
TD079 | TBD | TBD | TBD | TBD | MXWF Series | TBD | Terence.Musoni@Coopersurgical.com | TBD | TBD | TBD | TBD | Not started | YES | TBD | Is PSUR079 is relevant?
TD081 | PSUR081 | IIb | Medical Device | Fischer cone Biopsy Electrodes | See Plan Appendix | TBD | TBD | 2024-07-01 | 2025-08-31 | Annually | 2025-11-12 | Not started | YES | TBD
TD082 | PSUR082 | I, IIb | Medical Device | Pessary Product Family | See PLAN Appendix | Venkata SD | venkata.dommeti@coopersurgical.com | 2022-04-01 | 2024-03-31 | Annually | 2025-12-10 | Inprogress | YES | TBD | Finalizing Report and targeted to route next week - VSD 01AUG2025
TD089 | PSUR089 | III | Media | SAGE 1-Step | 67010010, 67010060 | Venkata SD | venkata.dommeti@coopersurgical.com | 2024-07-01 | 2025-06-30 | Annually | 2025-08-27 | In Progress | YES | TBD | NEEDED FOR SSCP
TD094 | PSUR202 | III | Media | Quinn's Sperm Washing Medium | (ART-1005) (ART-1006) | Pranavi | Pranavi.vutukuru@coopersurgical.com | 2024-01-01 | 2024-12-31 | Annually | 2025-01-29 | Stakeholder review | NO | TBD | Harish will take over
TD103 | PSUR103 | IIa, IIb | Medical Device | Micropipette Product Family | See PMS Plan | TBD | TBD | 2022-04-01 | 2024-03-31 | Annually | 2025-12-17 | Not started | YES | TBD
TD104 | TBD | TBD | TBD | TBD | BCT-HBA-10 | TBD | Terence.Musoni@Coopersurgical.com | TBD | TBD | TBD | TBD | Not started | YES | TBD | Is PSUR104 relevant?
TD105 | PSUR105 | IIa | Medical Device | Stripper Tips | See PMS Plan | Pranavi | Pranavi.vutukuru@coopersurgical.com | 2022-07-01 | 2025-06-30 | Annually | 2025-07-25 | Under Review | NO | TBD | Venkata will take over
TD114 | PSUR212 | III | Media | Human Serum Albumin (ART-3001) (ART-3003) | ART-3001, ART-3003 | Venkata SD | venkata.dommeti@coopersurgical.com | 2024-07-01 | 2025-06-30 | Annually | 2025-08-22 | Assigned | YES | TBD
TD114 | PSUR306 | III | Media | HSA 12 x 5 ml (GHSA-125) | GHSA-125, GHSA-005 | Jeff S | jeffrey.spivak@coopersurgical.com | 2022-07-01 | 2024-06-30 | Biennial | 2025-11-26 | Drafting | YES | TBD
TD117 | PSUR215 | III | Media | Quinn’s Advantage™ Thaw Kit | ART-8016, ART-8005-12, ART-8007-12, ART-8013-12 | Venkata SD | venkata.dommeti@coopersurgical.com | 2024-01-01 | 2024-12-31 | Annually | 2025-07-15 | Assigned - LATE Stakeholder review | NO | TBD | NEEDED FOR SSCP Report Completed waiting on risk files to be released - VSD
TD119 | TBD | TBD | TBD | TBD | C090120 Series | TBD | Terence.Musoni@Coopersurgical.com | TBD | TBD | TBD | TBD | Not started | YES | TBD
TD141 | PSUR141 | I, IIa | Medical Device | Zymot | TBD | TBD | TBD | 2018-01-01 | 2024-09-30 | Biennial | INVESTIGATE | Stakeholder Review | NO | TBD | Check Basma Comments
| PSUR007 |  |  | LoneStar Retractor Kit | See Plan Appendix |  |  | 2018-01-01 | 2022-12-31 | [5 empty] | PSUR007 Rev A is released in MC but not present in the schedule
| PSUR010 |  |  | Periodic Safety Update Report (PSUR) INCA | [10 empty] | Is this relevant PSUR?
| PSUR017 |  |  | PSUR for Hyaluronidase HEPES-HTF (ART-4007-A) | ART-4007-A, ART-4007-AA, ART-4007-AD | [9 empty] | Non EU-MDR product. PSUR017 Rev A is released in MC, do we need to update?
| PSUR038 |  |  | Quinn’s Advantage™ Serum Protein Substitute (ART-3011) | ART-3011 | [9 empty] | Non EU-MDR product. PSUR038 Rev A is released in MC, do we need to update?
| PSUR040 |  |  | Quinn’s Advantage™ Protein Plus Cleavage Medium | ART-1526-A | [9 empty] | Non EU-MDR product. PSUR040 Rev A is released in MC, do we need to update?
| PSUR042 |  |  | SAGE IVM Media Kit (ART-1600) | ART-1600 | [9 empty] | Non EU-MDR product. PSUR042 Rev A is released in MC, do we need to update?
|  |  |  | NGWS Next Gen Workstation | TBD | Jeff S | jeffrey.spivak@coopersurgical.com |  |  |  |  | Drafting |  |  | Medical Device
|  |  |  | TLI Time Lapse Incubator | TBD | Jeff S | jeffrey.spivak@coopersurgical.com |  |  |  |  | Drafting |  |  | Medical Device
|  |  |  | Wallace Aspiration Pump | TBD | Jeff S | jeffrey.spivak@coopersurgical.com |  |  |  |  | Drafting |  |  | Medical Device

## ISUI_00jnmykkz4sxdiktk (hidden)
TBD | 41 | Venkata SD
Harish G | 19 | TBD
Karen K | 17 | Karen K
Venkata SD | 14 | Jeff S
Heather H | 14 | Heather H
Jeff S | 13 | Harish G